## Slide 1
Operation-Aware Biomedical Text Simplification
Research question: does diagnosing WHICH edit a sentence needs before simplifying improve readability AND safety?
Diagnosis is validated
• UMLS jargon detection: 100% abstract coverage vs 86.8% morphological baseline (n=530, validated on random samples, 3-layer filtering)
• BioBERT classifier: 0.465 macro-F1, +9.7% over TF-IDF (0.424)
• DistilBERT: 0.392 macro-F1, -7.5% vs TF-IDF — general pretraining alone hurts
• Domain features (UMLS+numerical): +2.1-2.5% macro-F1 over TF-IDF, verified via controlled ablation + model coefficients, not just F1 delta
• Detector independence: 5 complexity detectors near-orthogonal (max phi=0.078)
Classifier progression (val, n=1,431)
Model | Macro-F1 | vs. TF-IDF
TF-IDF + LR | 0.424 | —
DistilBERT | 0.392 | -7.5%
BioBERT | 0.465 | +9.7%
TF-IDF + UMLS + Numerical | 0.445 | +2.1%
TF-IDF + all 8 features | 0.449 | +2.5%
What's still open
• Random sampling hides rare safety failures: random 50-sentence sample showed perfect (1.0) warning preservation across all baselines; warning-stratified stress test caught a real 5% drop in the Direct-LLM baseline — methodological finding, not noise
• Pseudo-label distribution mismatch: our weak-supervision labels (Sub 43.2% / Exp 34.4% / Gen 22.5%) diverge from Ondov et al.'s real annotated PLABA distribution (64.7% / 19.3% / 6.3%) — classifier's ~0.45 macro-F1 ceiling is partly a label-quality ceiling, not purely model capacity
The one number that doesn't exist yet
Operation-aware system vs. 3 baselines (SARI / warning / entity / numerical preservation) — this is the paper's central thesis test, and it has not been run yet. Diagnosis is proven; the generation comparison that proves diagnosis HELPS is the remaining experiment.

## Slide 2
Team Contributions (Last 4 Days) + Cross-Check Findings
Git history 07/24–07/28 — what each teammate shipped, and what my review corrected
Zihao — Full-corpus evaluation (07/26)
• Shipped: run_evaluation.py upgraded to full val set (n=1,141) + warning-stratified stress test (n=73); added entity/numerical preservation to metric suite
• Impact: Direct LLM highest SARI (24.37) but only baseline dropping below 1.0 on warning (0.959) and numerical (0.949) preservation — safety/readability trade-off now empirically visible
Son / Sophakotra — Classifiers + pipeline (07/27)
• Shipped: TF-IDF refactor to stateless Pipeline; DistilBERT + BioBERT classifiers; feature-augmented models (Track 2); operation router, constrained prompts, end-to-end Baseline-4 pipeline
• Impact: delivered the strongest single result in the project (BioBERT +9.7%) and the full generation architecture
My cross-check — 2 corrections to the narrative
• Track 2 "features don't help" was wrong: uncontrolled ablation (max_features 5,000 vs 50,000 mismatch between arms). Re-ran with matched settings → features DO help (+2.1-2.5%). Reverses a reported negative finding.
• Generation pipeline was silently broken: biobert_classifier.py never saved trained weights; end_to_end_pipeline.py was loading a fresh, UNTRAINED classifier (random 3-way head). Fixed: checkpoint saving + loud failure instead of silent wrong results. Also fixed CHV defaulting to a no-op placeholder.
Rishabh — no new commits this window
• Last shipped: 07/03 — data loader, CHV module, EDA visualizations, Intro/Data/Related-Work sections
• Outstanding: readability-vs-safety scatter plot, Related Work condensing, duplicate bib-key fix

## Slide 3
Remaining Work Before Submission
Priority-ordered — top item blocks the paper's central claim
1. Operation-aware vs. 3 baselines comparison — TOP PRIORITY, IN PROGRESS
• Status: BioBERT checkpoint re-training running now (bug fix from Slide 2). Once done: run full pipeline (BioBERT → CHV / constrained FLAN-T5) through Zihao's SARI/warning/entity/numerical harness against all 3 baselines.
2. Final test-set run
• All numbers so far (Track 1, Track 2, baselines) are on val — correct for model selection, but paper needs one frozen-config test-set run for headline numbers.
3. Rishabh's outstanding items
• Readability-vs-safety scatter plot (now unblocked on Zihao's side, blocked on item 1); condense Related Work; fix duplicate bib keys (Ondov2025/Attal2023 vs. ondov2025lessons/attal2023plaba)
4. Human evaluation
• Sample + rubric ready (20 sentences, warning-stratified, 3 outputs each) — needs to be run once operation-aware outputs exist.
5. Whole-team sections
• Introduction, Problem Statement, Conclusion, Ethics Statement, Main Idea (Sophakotra — needs to reflect corrected Track 1/2 story), final 8-page trim.
Timeline: diagnostic/classification work is complete and validated. Remaining work is execution (run the experiment, run on test set) plus writing — no open research risk, on track for Thursday deadline.